## Master
Geography | System | Actionable | Details | Timeline | Pending with | FPR - ITG | FPR - CG / Others | Date given by ITG (UAT) | ITG Comment on 16-10-2019 | Update as on 4-12-2019 | CR Status | Expected Closure Date for WIP Items (Dates to be stated in DD-MMM-YY) | Final Status (Choose options form drop down values) | Remarks
India | TM-AMLOCK | Duplicate credit card data in amlock\ | BRS Shared on 29th oct | UAT in progress |  | Siva | Toolika | ITG/ CG |  | Same is pending at CG to find the details of multiple customernames for single customerid and same is creating problem in Reporting(CTR,NTR) | BRS |  | Open | Still the approach is not yet finalised by CG to remove the duplicate data. 19/12/2019 -> Pending with ETL team. Arrange a call between Vidya (ETL), Toolika, Prakash & Siva
USA | SAS | FTI Audit observations of missing transactions | In discussion with M2I team |  |  | Supriya |  |  |  | Not an actionable for ITG, however item is being tracked for closure |  |  |  | Move this to BAU & Audit Tracker
India | TM-AMLOCK | Multiple Active Directory for Domains | BRS raised on 28th Nov | UAT in progress, will provide URL for CG testing | ITG | Surya/Manohar |  | Priority |  | We deployed the patch in UAT. Once UAT testing is done by ITG. Same will be confirmed by CG Team | Live Deployment | 2019-12-10 | Closed | 24-dec-2019 moved to live
Canada | TM-AMLOCK | Spurt in Legacy alerts | RCA for sPURT to be identified | ITG to investigate | ITG |  | Khushboo | Priority | [5 empty] | 19/12/2019 ->Prakash spoke to Surya. Not pending with ITG. CG team to invetsiigate further
Singapore | TM-AMLOCK | File Upload Log report: Customer count in Legacy logs to be recitified | Awaiting UAT release | Awaiting UAT release | ITG | Vishnu | Shrishti | Priority |  |  | BRS |  | Open | 19/12/2019 -> UAT to be released 03-01-2020 -> BRS raised for correcting customer count.
India | TM-Migration | Out of amlock adhoc -Source system integartion (84-Scenarios) | At initial stage |  |  |  |  | CG-Tech | Priority2 | Toolika |  |  |  | 19/12/2019 -> To be checked with Prakash
India | NS-AMLOCK | Insta trade: Name screening report based on reference number | Insta trade: Name screening report based on reference number |  | Feasibility check ongoing |  |  | Ops/ITG | Priority2 |  |  |  |  | 19/12/2019 -> To be checked with Prakash
India | TM-AMLOCK | STR-REGeneration | STR Generation is in progress | WIP | ITG |  | Shital | Priority |  |  | CG Signoff for Prod |  | Closed | 19/12/2019 -> SET 1 is COMPLETED for 600 alerts SET2 is COMPLETED for 5141 alerts(Chetan from CG to confirm on same) There are no pending alerts for regeneration.
India | TM-AMLOCK | New Alert :RFI for drug business | Duplicate credit card data in amlock\ | It requires architecting current solution | ITG |  |  | Priority | Changes are given to vendor for code feasibility,same has to be implemented on UAT4.3 FPR:Shital(CG),Siva(ITG) | Same has been taken up with Srikanth(Vendor). Feasibility check will be initiated from there end once 4.3 is live. |  |  | Deferred | 19/12/2019 -> Same has been taken up with Srikanth(Vendor). Feasibility check will be initiated from there end once 4.3 is live.
Singapore | SAS | ETL development Bene stated location | BRS is shared | Rikesh to arrangemapping from I-core MIS team | ITG |  | Shristi | Priority |  |  | BRS |  | Open | 19/12/2019 -> Rikesh has to arrange call with Icore & ETL teams along with Prakash
USA | SAS | Case aging Report | BRS Raised | Hotfix 7 is deployed in US Dev environment and the issue regarding below 3 points mentioned in the mail trial are resolved. However there are certain issues and new functionalities & Capability changes that are raised to SAS Consulting & Tech Support team. We will release the setup for UAT once we receive resolution . Observations: 1)Any action will be enabled only on Locking the entity/case- this will disable users to act on same entity / case simultaneously. 2)Analyst unable to add comment on case without edit capability (this would impact the US maker checker approach as edit capability should not be given to Analyst). 3)Accessing notes of a closed case when any entity in triage is opened is resulting in closure event (observed in all Geo)- is not resolved. | ITG | Supriya | Santosh | Priority |  |  |  |  | Closed | 19/12/2019 -> Requirement dropped. Ravi from US Compliance has confirmed
Hongkong | NS-AMLOCK | HK NS Unsubscribed PEP UAT |  |  |  | Naveen |  |  |  | Signoff pending from CG team | Live Deployment | 2019-12-16 | Closed | 19/12/2019 -> Pending with DWH & CG
India | TM-AMLOCK | Rules RFI 9 and RFI 10: | Kept on Hold till completion of AMLOCK INDIA 4.3 UAT. | Observation shared with ITG onhold for other critical items |  | Siva |  | ITG | Priority2 | Kept on Hold till completion of AMLOCK INDIA 4.3 UAT.Pending at CG |  |  | Closed | 19/12/2019 -> Pending with CG
Hongkong | TM-AMLOCK | Correction of count of records in Data Import Log by MI | Count of records processed, updated and inserted need to be corrected in AMLOCK | UAT delivery awaited from ITG. | ITG | Vishnu |  | Priority |  | UAT deleivered. Khushboo to give sign-off. | CG Signoff for Prod |  | WIP | 19/12/2019 -> Pending CG for UAT sign-off 03/01/2020 -> CR Pending(Whiziable) with Security assignment team.
India | NS-AMLOCK | NTS Integration with AMLOCK | UAT Sign off provided on 05th Dec 2019 | UAT Sign of provided. Pending for Golive | ITG |  | Vishal | Priority |  |  | CG UAT |  | Closed | 19/12/2019 -> Open for go-live. Approval from CG pending. Not pending at ITG
All | NS-AMLOCK | Addition of two new keywords(28th August) |  | Moved to production | ITG |  | Vishal | Priority |  |  |  |  | Closed | 19/12/2019 -> Moved to production
Hongkong | TM-AMLOCK | PEP: Unsubscribed Keywords PEP are not appearing in match records | Observations shared with ITG. UAT in progress | UAT Sign of provided. Pending for Golive | ITG | Vishnu/Surya | Vishal | Priority |  |  | CG Signoff for Prod |  | WIP | 19/12/2019 -> Has moved to production 03/01/2020 -> CR Pending(Whiziable) with Security assignment team.
Hongkong | TM-AMLOCK | Audit: Retro Generation on missed transactions | Audit period transaction data till date to be compared to identify missed transactions. | BRS is raised | ITG | Hari | Chandan | Priority | [5 empty] | 19/12/2019 -> Hari to revert on txn recon aspect
UK | Web Integraion | UK:Digi APP DOB Parameter to be used in Account opening Web Integration | Vendor to explore the Feasibility and confirm BRS is shared. | Vendor Delivery awaited by | ITG | Sampath |  | Priority |  | FSD sign-off pending from CG | CR Initiated |  | WIP | 19/12/2019 -> FSD sign-off pending from CG
India | TM-AMLOCK | 10 system live screening | 1. Tranche III non conformity 2.large products like finagri, PCMS 3.need -IT infra support 4.high volume of alerts anticipated Forum to take a discussion on whether we channelize efforts in developing in AMLOCK or included in phase II of migration of new NS systems. Risk: RBI con-conformity |  |  |  | Prakash Raulo |  | Hold | Toolika/Shital |  |  | Open | 19/12/2019 -> For clarifications with Prakash Raulo
Singapore | SAS | Reports funcationality not working properly | Logs are being taken on a daily basis | Call scheduled with all stakeholders on 13th | ITG/BIS | Supriya | Shristi | Priority |  |  |  |  | Closed | 19/12/2019 -> CG team (Shriisti) to arrange call with busines users
India | India-ETL | CBWTR - Retail Remittances | BRS in process |  | ITG/ CG-Tech |  | Shristi | Priority | [5 empty] | 19/12/2019 -> CG (Toolika) to revert. Currently, item is not with ITG
India | India-ETL | CBWTR -Treasury | Office Account Cash transactions upload in a dailly mode. | Mapping Document in progress. Timelines ot be decided | ITG/CG-Tech | Rikesh | Shristi | Priority |  |  |  |  | WIP | 19/12/2019 -> CG (Shrishti) to revert. Currently, item is not with ITG
USA | SAS | LOOK BACK : Solution from SAS | ICICI_03_Sudden_Surge_Act_High/Low/Medium to be re-run since 29 Nov 2017 till 01 Jun 2019 (m21 customers) Rerun for Whole Sale Banking since 01 Jun 2018 till 01 Jun 2019. | Server to be released to ARC by 20 Dec 2019 | ITG |  |  | Priority |  |  | FSD Reviewed |  | WIP | 19/12/2019 -> Approach is finalized and commercials for the development shared
Canada | TM-AMLOCK | Auto closure Logic for High Legacy Alerts | BRS raised on 6th Nov, 2019. UAT is in progress | Post one round of UAT Defects are raised with ITG | ITG | Vishnu | Vishal/khushboo | Priority |  |  | CG Signoff for Prod | 2020-01-06 | WIP | 03/01/2020 -> Due to year and month end support team not doing deployment will deploy in live by 6th Jan 2020
UK | TM-AMLOCK | Auto closure Logic for High Legacy Alerts | BRS raised on 6th Nov, 2019. UAT is in progress | Post one round of UAT Defects are raised with ITG | ITG | Vishnu | Vishal | Priority |  |  | CG UAT |  | WIP | 03/01/2020 -> CG asked for more testcases which is provided. Pending with CG for sign off to production
India | NS-AMLOCK | Multiple Active Directory for Domains | BRS raised on 28th Nov | UAT in progress, will provide URL for CG testing | ITG | Sravan / Naveen/COE Support |  | Priority |  | We deployed the patch in UAT. Once UAT testing is done by ITG. Same will be confirmed by CG Team | CG UAT |  | WIP | 03/01-/2020->UAT Testing pending with CG team.
India | TM-AMLOCK | 2lakhs alerts got generated due to duplicate in reference master | 1. 65K Alerts closed, .1.3 lacs alert are pending to exclude for auto supression. 2. Alert Regeneration is in progress. 3. Post Alert generation counts to be shared with Kevin | Awaiting Closure date from ITG | ITG | Siva |  | Priority | FPR VAMSHIDAR and prakash.Same will be initiated from ITG on 17-10-2019. Dependency are there on same as we will generate the alerts in phase wise when the system is free from daily and monthly activities | UPDATED DATA IS PROVIDED IN BACKDATED GENERATION ALERT WISE STATISTICS SHEET | ITG UAT |  | WIP | 03-01-20. Total 9 alerts in line where for 8 alerts generation is completed and still one in progress.Same will be delivered in before 10th Jan 2020
India | TM-AMLOCK | Backdated alert genearation | Backdated alert genearation | Backdated alert genearation for 19 scenarios Rules implemented in April-May 2019. These alerts are to be generated from October 2018. | ITG to generate alerts.ITG propose for front-end | Vamsidhar / Siva |  | CG | Priority | Same is in process,Break up for same is attached in BACKDATED GENERATION ALERT WISE. Out of 9 alerts - | ITG UAT | 2020-01-10 | WIP | 03-01-20. Total 9 alerts in line where for 8 alerts generation is completed and still one in progress.Same will be delivered in before 10th Jan 2020
USA | Pelican | KB Tuning Report has been received from vendor currently under review, queries are been raised with Pelican team for clarification. | UAT to be released by 15 Nov, Go live by 25 Nov | Pending for UAT Delivery. | ITG |  |  | Priority |  | Following up with Pelican and still working on the API tool to process the bulk request | ITG UAT | 2020-01-18 | WIP | UAT to be released by 08 Jan, Go live by 18 Jan
Hongkong | TM-AMLOCK | NRISR file to be treated as a Mandatory file during Upload. | Revised BRS raised on 1st Nov, 2019. FSD sign off given on 18th Nov, 2019. | ITG to share the UAT delivery timeline | ITG |  |  | Priority | FSD in not yet finalised from 3i. FPR:Khushboo(CG),HARI(ITG) | We will deploy the patch in UAT on 28/11/2019 FPR:Khushboo(CG), Hari (ITG) |  |  | Closed
Hongkong | TM-AMLOCK | Transaction monitoring of USD-EURO Clearing transactions: revising the logic to sum of transactions instead of individual transactions Swift transactions flow(MT 202 COV) | BRS raised - make it alert based. BRS shared with ITG on 07 Aug 2019, FSD sign off received | The patch will be delivered on 22nd Nov 2019 by ITG | ITG | Hari | Khushboo | Priority | UAT delivery on 22nd Nov, 2019FPR:Khushboo(CG),HARI(ITG) | We had deployed the patch in UAT on 22/11/2019. FPR:Khushboo(CG), Hari (ITG) Currently in UAT Testing(basic testing at coding level) | CG UAT |  | WIP | 03/01/2020 -> CG UAT PENDING 2 changes pending with vendor-3I for existing logic.
USA | Pelican | Fincen: Changes to consider Active customer List | Fincen Screening to consider all the customers except the closed customers which are closed Prior to one Year. | BRS is shared with ITG. Awaiting delivery date from ITG | ITG | Vamsi |  | Priority |  | We are following up with Pelican and we will update you on this by 25-Nov-2019 | BRS | 2020-01-13 | WIP | Fincen Screening to consider all the customers except the closed customers which are closed Prior to one Year. We are following up with Pelican and we will update you on this by 13-Jan-2020
USA/UK/SG | SAS | Once case is closed without RFI, still we can able to change the status. | Application team will deploy Hotfix as a solution | Awaiting UAT delivery | ITG | Supriya |  | Priority |  | Hotfix 7 is deployed in US Dev environment and the issue regarding below 3 points mentioned in the mail trial are resolved. However there are certain issues and new functionalities & Capability changes that are raised to SAS Consulting & Tech Support team. We will release the setup for UAT once we receive resolution . Observations: 1)Any action will be enabled only on Locking the entity/case- this will disable users to act on same entity / case simultaneously. 2)Analyst unable to add comment on case without edit capability (this would impact the US maker checker approach as edit capability should not be given to Analyst). 3)Accessing notes of a closed case when any entity in triage is opened is resulting in closure event (observed in all Geo)- is not resolved. |  |  | Closed
USA/UK/SG | SAS | Post closure of case, case aging has to stop and freeze. | Application team will deploy Hotfix as a solution | Awaiting UAT delivery | ITG | Supriya |  | Priority |  | Hotfix 7 is deployed in US Dev environment and the issue regarding below 3 points mentioned in the mail trial are resolved. However there are certain issues and new functionalities & Capability changes that are raised to SAS Consulting & Tech Support team. We will release the setup for UAT once we receive resolution . Observations: 1)Any action will be enabled only on Locking the entity/case- this will disable users to act on same entity / case simultaneously. 2)Analyst unable to add comment on case without edit capability (this would impact the US maker checker approach as edit capability should not be given to Analyst). 3)Accessing notes of a closed case when any entity in triage is opened is resulting in closure event (observed in all Geo)- is not resolved. |  |  | Closed
India | NS-AMLOCK | Removal of PEP data : Remiitance and Trade |  | Awatiing Uat Delivery | ITG |  |  | Priority |  | Release in UAT expected on 27-Dec-2019 | ITG UAT | 2019-12-27 | WIP
USA | Pelican | CIB Integration with Business FX | Integration of Business FX with Pelican | Revised BRS to be received from IBG-Product team | ITG | Vamsi |  | Priority |  | We are reviewing the BRS and we are planning to discuss with Compliance team on 26-Nov-2019 | BRS | 2020-01-08 | WIP | We are reviewing the BRS and we are planning to discuss with Compliance team on 08-Jan-2020
Bahrain | TM-AMLOCK | Validation control for exception in alert generation due to missing customer/account details | BRS is shared | Awaiting FSD from 3i-Info tech | ITG | Surya |  | Priority | FSD in not yet finalised from 3i. FPR:Khushboo(CG),HARI(ITG) | We will deploy the patch in UAT on 28/11/2019 FPR:Khushboo(CG), Hari (ITG) 4/12/2019 -> FSD finalized, patch development pending with 3i | BRS | 2019-12-20 | WIP
India | TM-AMLOCK | Tomba Singh: Data extraction of Closed Legacy Alerts where likely true match are closed (DOB/PAN Match) | Replicate the data in temporary db and execute the query instead of production database. | ITG to explore the feasibility and confirm | ITG | Siva |  | Priority | Not feasible,Please close this observation | Not feasible as per Vendor's report. Please close this observation |  |  | Closed
IBG | SAS-ETL | Purging policy for Landing and staging |  |  | ITG |  |  | Priority | Purging Policy will be raised | I-Memo has to be raised by our team. | BRS |  | Open
India | TM-AMLOCK | Office Account Cash transactions upload in a dailly mode. | Office Account Cash transactions upload in a dailly mode. | Office Account transaactions would be enabled in MIS282 format and to be uploaded in Amlock | Moved to Production on Nov | Siva |  | ITG | Priority | UAT is done in 4.3 same can be used for present production , ISSUE:TRASACTIONID IS NOT MATCHED with present production and same is communicated with CG. CR-553-129705, Same is deployed in production on 18/NOV/2019. |  |  | Closed
India | TM-AMLOCK | Testing CCR reporting to FIU for AMLOCK 3.7 | Testing CCR reporting to FIU for AMLOCK 3.7 | UAT testing done.UAT sign off received. | CR-553-128243 , Moved to Production on 11 Oct 2019 | Siva |  | ITG | Priority | CR-553-128243 , Moved to Production on 11 Oct 2019 |  |  | Closed
India | TM-AMLOCK | Auto closure Logic for High Legacy Alerts | Auto Closure Logic for spurt in Legacy Alerts | Pending alerts ,12 lac BRS is shared, FSD signoff provided on 9th aug. Incremental data moved to production on 5th Nov. | Moved to Production | Vishnu / Siva | Vishal | Priority |  | CR-553-129354,Moved to production. Backdated alerts also closed using the same logic. | Live Deployment | 2019-11-05 | Closed
India | TM-AMLOCK | New column "Issuspended" to be incorporate in customer master which is being used for legacy alerts | New column "Issuspended" to be incorporate in customer master which is being used for legacy alerts | 1. Sign off on ETL changes has been given to DWH team to be taken up after 29/JUL/2019 2. Sign off on Amlock Changes is given to Amlock team, to move to production after ETL Changes. 3. One time refresh of Closed customer ids need to be done in Amlock India. | Move to production on 20th August 2019 | Surya / Siva |  | ITG | 2019-08-20 | Move to production on 20th August 2019 |  |  | Closed
India | TM-AMLOCK | 65 alerts auto suppression of false positives | 65 alerts auto suppression of false positives | Requirement shared – Oct 01 Sign off provided on FSD-Jan 04 UAT received-May 15 UAT in process. MErged with Version upgrade and tested in new version. | Merged with Amlock Version Upgrade. Testing in both versions completed successfully | Siva |  |  | Closed | Merged with Amlock Version Upgrade of 4.3. Testing in both versions completed successfully. Same will be in production for 4.3. |  |  | Closed
India | TM-AMLOCK | RAS link is not accessible without user ID | RAS link should be accessible without ID | UAT deployment awaited |  |  |  |  | Closed |  |  |  | Closed
India | TM-AMLOCK | CTR Incremental CTR for November 2018 | Requirement shared for this audit query ITG to find a solution for identifying incremental cash transactions | Approach to be finalised-July end. |  | Siva | Ria |  | Closed | Incremental CTR is given for month of NOV 2018,Same is closed. |  |  | Closed
India | TM-AMLOCK | Large value non-cash transactions in CAA accounts Requirement | CG-Prod to configure the threshold parameters | CG-Prod share timeline |  | Siva / Manohar |  |  | Closed | Moved to production |  |  | Closed
India | TM-AMLOCK | 1.Little or No Withdrawals from account for Business Purposes. live 2.Accounts funded by negotiable instruments in round denominations- configuration pending | Live on August 01, 2019 | Live on August 01, 2019 |  | Siva |  | CG-Product | Closed | Moved to production |  |  | Closed
India | TM-AMLOCK | TBML: Wash Sales rules. Modification & addition of new scenario | Live on August 01, 2019 | Live on August 01, 2019 |  | Siva |  | CG-Product | Closed | Moved to production |  |  | Closed
India | TM-AMLOCK | Productivity Enhancements for TMU: Phase I Customer Search filter Bulk escalate at level one |  | closed |  | Siva |  |  | Closed | Moved to production |  |  | Closed
India | TM-AMLOCK | Modification: Sudden increase in cash deposits in Accounts held by High Risk Customers |  | Closed |  | Siva |  |  | Closed | Moved to production |  |  | Closed
India | TM-AMLOCK | Numerous Low Non Cash Deposit Transactions Leading to Large Accumulation |  | Closed |  | Siva |  |  | Closed | Moved to production |  |  | Closed
India | TM-AMLOCK | New FIU RFI Phase I: 14 Phase II: 4 | Phase I: RFI FIU scenarios – 20-Live Phase II: Dependent on counterparty data, ETL level change | Phase I- closed Phase II- dependent on counterparty data |  |  |  | CG-Product | Priority2 | Phase I- closed Phase II- dependent on counterparty data(SAME IS HOLD AT CG) |  |  | Closed
India | TM-AMLOCK | NTR- section 8 companies | Data received from BIU, under analysis | Aniket from BIU to validate the data and get back |  |  |  | BIU | 2019-10-01 | Pending with CG |  |  | Closed
India | TM-AMLOCK | CBWTR (Cross Border Wire Transfer Report)-Automation | Scoping work in Progress, BRS to be shared |  |  |  |  | CG-Tech | Priority | Yet to be finalised in 4.3 | BRS |  | Open
India | TM-AMLOCK | Missing customer types Issue for Finnacle | BRS Shared on 29th oct | UAT Signed off. Go live date - 19th november |  | Siva |  | DWH |  | One time dump from CRM module customer types is inserted in to AMLOCK system.Automated flow is pending with CG (Toolika) |  |  | Closed
India | TM-AMLOCK | Missing Product type codes in credit cards data | BRS Shared and CR Raised with DWH | Timelines awaited from DWH |  | Siva |  | DWH |  | Development is pending at DWH level and CG yet to finalise the flow |  |  | Closed
Bahrain | NS-AMLOCK | Bahrain NS Error message while file upload UAT | Port Opening |  |  | Naveen |  |  |  | pending at support team for port opening and CG team |  |  | Closed
India | NS-AMLOCK | Matches are coming for NULL value when HULL is screened |  |  |  | Naveen |  |  |  | UAT released signoffpending from CG team |  |  | Closed
Singapore | NS-AMLOCK | AML Analytics Audit. Files prepared for uploading (sg) |  |  |  | Naveen |  |  |  | CG team should inform us on the thematic review | BRS |  | Open
India | NS-AMLOCK | deactivation of denylist for 1Lakh + records India NS and TM |  |  |  | Naveen |  |  |  | 3/12/19->Activity pending with ITG 4/12/19-> Pending with CG for data confirmation | CG UAT |  | Open
India | NS-AMLOCK | 8 reports released to UAT CG team | User was unable to download report from front end |  |  | Naveen |  |  |  | Released in UAT, however CG team needs to know the RCA of the bug fix / issue fix | Live Deployment | 2019-12-25 | Closed
Bahrain | Web Service T & T+1 | Final patch expected in UAT | Post UAT, trial run needs to be run |  |  | Sampath |  |  |  | Patch exppected on 4-Dec-19 | ITG UAT | 2019-12-10 | WIP
India | TM-AMLOCK | Spurt in Legacy alerts | Spurt in Legacy alerts | List Rationalisation Closed customer id and Auto Closure is taken up separately | testing for point 1 and 2 done. ITG to move CR into production. | Surya |  | ITG | Priority2 | CG to revert with details of list, discussion pending | BRS |  | Open | CG to revert with details of list, discussion pending
All geographies | TM-AMLOCK | Multiple Active Directory for Domains | BRS raised on 28th Nov | UAT in progress, will provide URL for CG testing | ITG | Surya |  | Priority |  | We deployed the patch in UAT. Once UAT testing is done by ITG. Same will be confirmed by CG Team | ITG UAT | 2019-12-15 | WIP
All geographies | NS-AMLOCK | Multiple Active Directory for Domains | BRS raised on 28th Nov | UAT in progress, will provide URL for CG testing | ITG | Sravan / Naveen/ Surya/COE Support |  | Priority |  | We deployed the patch in UAT. Once UAT testing is done by ITG. Same will be confirmed by CG Team | ITG UAT |  | WIP
Canada | TM-AMLOCK | Legacy Alert Spurt: 1. Closed Customer ID implementation 2. List Rationalisation | 1) BRS and TC made on 12 July, 2019 CR raised by Canada Compliance. 2) List and BRS shared with ITG on 7Th August | Live deployment done on 13th Nov, 2019 | ITG | Hari |  |  | Live deployment date : 13th Nov, 2019 FPR:Khushboo(CG),Hari,swati(ITG) | Live deployment completed |  |  | Closed
Bahrain | TM-AMLOCK | Bahrain Legacy generation for suspended Customer Id. | Arrange the Fresh full dump of Bahrain Customers . To compare with the 17 Sep dump to identify the count of difference. | Full dump refresh will be done by 21 Nov 2019 | MIS | Hari |  | 2019-11-21 |  | we moved complete customer dump into live |  |  | Closed
Bahrain | TM-AMLOCK | Validation for Exception before Alert generation | BRS raised on 25th sep, 2019. 14-10-2019. FSD sign off given. | UAT in progress | ITG/CG-TECH | Hari |  | Priority |  | We will deploy the patch in UAT on 05/12/2019. FPR:Khushboo(CG), Hari (ITG) | CG UAT |  | WIP | 03/01/2020>> pending with CG
Canada | TM-AMLOCK | Credit card alert generation under 7 alert rules | Data validation going on for bulk upload of files in LIVE. Validation completed for files from Post Date 30th Jul to 20th Aug and alert generation in Daily alert rules. | Need some clarity from ITG for monthly alert rules. | ITG/CG-TECH | Hari |  |  |  | we had uploaded the credit card account,customer and transaction file and we had generated the alerts . we have checked daily rules alerts generation and alerts generated properly . Right now we are checking monthly rules alerts generation. except 2 monthly rules remaing two rules alerts generation is good. | FSD Reviewed |  | WIP | 03/01/2020 ->FSD signoff pending with CG
USA | Pelican | Legacy Alert back end closure: Due to Technical Error Legacy alert got triggered. | Legacy alert generation was disabled due to High FPR, Due to technical issue the alerts got triggered. Post memo approval the alerts need to be closed from back-end. | Post KBTuning it will be released in UAT. | ITG |  | Santosh | Priority |  |  | CR Initiated | 2020-01-08 | WIP | Legacy alert generation was disabled due to High FPR, Due to technical issue the alerts got triggered. Post memo approval the alerts need to be closed from back-end. We need to test this in UAT environment and we will provide the timeliness on this on 08-JAN-2020
UK | NS-AMLOCK | AML Analytics Audit | Awaiting files from AML Analytics | Testing to be carried on 16 DEC 2019 | UK Operations/ITG |  | Vishal | Priority
Canada | TM-AMLOCK | Customer ID Based Rules including change in logic in Rule High Transaction Volume. | BRS raised to ITG. Revised FSD sign off given. | Awatiing issue fix from ITG | ITG | Hari | Khushboo | Priority |  |  | CG UAT |  | WIP | 03/01/2020 ->total 4 alerts rules 2 rules are pending with CG-UAT and 2 rules are pending with 3i
USA | SAS | M2I duplicate SSN counts | Details shared with ITG team. (Covered in row 6) | ITG to check | DWH/ITG | Supriya | Khushboo/Santosh | Priority
USA | SAS | For commercial customer SSN no is appearing instead of TIN no. | Data validation for Existing customer is remaining. M2I tech team need to provide the TIN numer for commercial account number | ITG to refresh the SOLR | ITG |  | Santosh | Priority
India | India-ETL | CBWTR- Credit cards | BRS Shared on 21st august Mapping details received from CC BTG. Validation pending. | Revised Mapping document Awaited | ITG | Rikesh | Toolika | Priority
India | India-ETL | CBWTR - Travel Cards | BRS Shared on 21st august. First draft of mapping document shared by Rikesh. | Revised Mapping document Awaited | ITG | Rikesh | Toolika | Priority
USA/UK/SG | SAS | Unable to retrieve historical transactions at Case Level | Hotfix 7 is deployed in US Dev environment SIT is in progress | Awaiting UAT delivery | ITG | Supriya |  | Priority
Hongkong | TM-Migration | Amlock 4.3 migration | [5 empty] | Priority |  |  | FSD Reviewed |  | WIP | 03-01-20-> FSD signoff pending with CG
Bahrain | TM-AMLOCK | Unable to generate Complete alert report Pending alert report. | New Pending Alerts and Completed Alerts Report for Amlock Bahrain TM. |  |  | Vishnu | Santosh | Priority |  |  | CG UAT |  | WIP | 03-01-20-> UAT pending with CG

## For Dashboard
Geography | System | Actionable | Details | Timeline | Pending with | FPR - ITG | FPR - CG / Others | Date given by ITG (UAT) | ITG Comment on 16-10-2019 | Update as on 4-12-2019 | CR Status | Expected Closure Date for WIP Items (Dates to be stated in DD-MMM-YY) | Final Status (Choose options form drop down values) | Remarks
India | TM-AMLOCK | Duplicate credit card data in amlock\ | BRS Shared on 29th oct | UAT in progress |  | Siva | Toolika | ITG/ CG |  | Same is pending at CG to find the details of multiple customernames for single customerid and same is creating problem in Reporting(CTR,NTR) | BRS |  | Open | Still the approach is not yet finalised by CG to remove the duplicate data. 19/12/2019 -> Pending with ETL team. Arrange a call between Vidya (ETL), Toolika, Prakash & Siva
USA | SAS | FTI Audit observations of missing transactions | In discussion with M2I team |  |  | Supriya |  |  |  | Not an actionable for ITG, however item is being tracked for closure |  |  | Closed | Move this to BAU & Audit Tracker
India | TM-AMLOCK | Multiple Active Directory for Domains | BRS raised on 28th Nov | UAT in progress, will provide URL for CG testing | ITG | Surya/Manohar |  | Priority |  | We deployed the patch in UAT. Once UAT testing is done by ITG. Same will be confirmed by CG Team | Live Deployment | 2019-12-10 | Closed | 24-dec-2019 moved to live
Canada | TM-AMLOCK | Spurt in Legacy alerts | RCA for sPURT to be identified | ITG to investigate | ITG |  | Khushboo | Priority | [5 empty] | 19/12/2019 ->Prakash spoke to Surya. Not pending with ITG. CG team to invetsiigate further
Singapore | TM-AMLOCK | File Upload Log report: Customer count in Legacy logs to be recitified | Awaiting UAT release | Awaiting UAT release | ITG | Vishnu | Shrishti | Priority |  |  | BRS |  | Open | 19/12/2019 -> UAT to be released 03-01-2020 -> BRS raised for correcting customer count.
India | TM-Migration | Out of amlock adhoc -Source system integartion (84-Scenarios) | At initial stage |  |  |  |  | CG-Tech | Priority2 | Toolika |  |  |  | 19/12/2019 -> To be checked with Prakash
India | TM-AMLOCK | STR-REGeneration | STR Generation is in progress | WIP | ITG |  | Shital | Priority |  |  | CG Signoff for Prod |  | Closed | 19/12/2019 -> SET 1 is COMPLETED for 600 alerts SET2 is COMPLETED for 5141 alerts(Chetan from CG to confirm on same) There are no pending alerts for regeneration.
India | TM-AMLOCK | New Alert :RFI for drug business | Duplicate credit card data in amlock\ | It requires architecting current solution | ITG |  |  | Priority | Changes are given to vendor for code feasibility,same has to be implemented on UAT4.3 FPR:Shital(CG),Siva(ITG) | Same has been taken up with Srikanth(Vendor). Feasibility check will be initiated from there end once 4.3 is live. |  |  | Deferred | 19/12/2019 -> Same has been taken up with Srikanth(Vendor). Feasibility check will be initiated from there end once 4.3 is live.
Singapore | SAS | ETL development Bene stated location | BRS is shared | Rikesh to arrangemapping from I-core MIS team | ITG |  | Shristi | Priority |  |  | BRS |  | Open | 19/12/2019 -> Rikesh has to arrange call with Icore & ETL teams along with Prakash
USA | SAS | Case aging Report | BRS Raised | Hotfix 7 is deployed in US Dev environment and the issue regarding below 3 points mentioned in the mail trial are resolved. However there are certain issues and new functionalities & Capability changes that are raised to SAS Consulting & Tech Support team. We will release the setup for UAT once we receive resolution . Observations: 1)Any action will be enabled only on Locking the entity/case- this will disable users to act on same entity / case simultaneously. 2)Analyst unable to add comment on case without edit capability (this would impact the US maker checker approach as edit capability should not be given to Analyst). 3)Accessing notes of a closed case when any entity in triage is opened is resulting in closure event (observed in all Geo)- is not resolved. | ITG | Supriya | Santosh | Priority |  |  |  |  | Closed | 19/12/2019 -> Requirement dropped. Ravi from US Compliance has confirmed
Hongkong | NS-AMLOCK | HK NS Unsubscribed PEP UAT |  |  |  | Naveen |  |  |  | Signoff pending from CG team | Live Deployment | 2019-12-16 | Closed | 19/12/2019 -> Pending with DWH & CG
India | TM-AMLOCK | Rules RFI 9 and RFI 10: | Kept on Hold till completion of AMLOCK INDIA 4.3 UAT. | Observation shared with ITG onhold for other critical items |  | Siva |  | ITG | Priority2 | Kept on Hold till completion of AMLOCK INDIA 4.3 UAT.Pending at CG |  |  | Closed | 19/12/2019 -> Pending with CG
Hongkong | TM-AMLOCK | Correction of count of records in Data Import Log by MI | Count of records processed, updated and inserted need to be corrected in AMLOCK | UAT delivery awaited from ITG. | ITG | Vishnu |  | Priority |  | UAT deleivered. Khushboo to give sign-off. | CG Signoff for Prod |  | WIP | 19/12/2019 -> Pending CG for UAT sign-off 03/01/2020 -> CR Pending(Whiziable) with Security assignment team.
India | NS-AMLOCK | NTS Integration with AMLOCK | UAT Sign off provided on 05th Dec 2019 | UAT Sign of provided. Pending for Golive | ITG |  | Vishal | Priority |  |  | CG UAT |  | Closed | 19/12/2019 -> Open for go-live. Approval from CG pending. Not pending at ITG
All | NS-AMLOCK | Addition of two new keywords(28th August) |  | Moved to production | ITG |  | Vishal | Priority |  |  |  |  | Closed | 19/12/2019 -> Moved to production
Hongkong | TM-AMLOCK | PEP: Unsubscribed Keywords PEP are not appearing in match records | Observations shared with ITG. UAT in progress | UAT Sign of provided. Pending for Golive | ITG | Vishnu/Surya | Vishal | Priority |  |  | CG Signoff for Prod |  | WIP | 19/12/2019 -> Has moved to production 03/01/2020 -> CR Pending(Whiziable) with Security assignment team.
Hongkong | TM-AMLOCK | Audit: Retro Generation on missed transactions | Audit period transaction data till date to be compared to identify missed transactions. | BRS is raised | ITG | Hari | Chandan | Priority | [5 empty] | 19/12/2019 -> Hari to revert on txn recon aspect
UK | Web Integraion | UK:Digi APP DOB Parameter to be used in Account opening Web Integration | Vendor to explore the Feasibility and confirm BRS is shared. | Vendor Delivery awaited by | ITG | Sampath |  | Priority |  | FSD sign-off pending from CG | CR Initiated |  | WIP | 19/12/2019 -> FSD sign-off pending from CG
Singapore | SAS | Reports funcationality not working properly | Logs are being taken on a daily basis | Call scheduled with all stakeholders on 13th | ITG/BIS | Supriya | Shristi | Priority |  |  |  |  | Closed | 19/12/2019 -> CG team (Shriisti) to arrange call with busines users
USA | SAS | LOOK BACK : Solution from SAS | ICICI_03_Sudden_Surge_Act_High/Low/Medium to be re-run since 29 Nov 2017 till 01 Jun 2019 (m21 customers) Rerun for Whole Sale Banking since 01 Jun 2018 till 01 Jun 2019. | Server to be released to ARC by 20 Dec 2019 | ITG |  |  | Priority |  |  | FSD Reviewed |  | WIP | 19/12/2019 -> Approach is finalized and commercials for the development shared
Canada | TM-AMLOCK | Auto closure Logic for High Legacy Alerts | BRS raised on 6th Nov, 2019. UAT is in progress | Post one round of UAT Defects are raised with ITG | ITG | Vishnu | Vishal/khushboo | Priority |  |  | Live Deployment | 2020-01-06 | Closed | 03/01/2020 -> Due to year and month end support team not doing deployment will deploy in live by 6th Jan 2020
UK | TM-AMLOCK | Auto closure Logic for High Legacy Alerts | BRS raised on 6th Nov, 2019. UAT is in progress | Post one round of UAT Defects are raised with ITG | ITG | Vishnu | Vishal | Priority |  |  | CG UAT |  | WIP | 03/01/2020 -> CG asked for more testcases which is provided. Pending with CG for sign off to production
India | NS-AMLOCK | Multiple Active Directory for Domains | BRS raised on 28th Nov | UAT in progress, will provide URL for CG testing | ITG | Sravan / Naveen/COE Support |  | Priority |  | We deployed the patch in UAT. Once UAT testing is done by ITG. Same will be confirmed by CG Team | CG UAT |  | WIP | 03/01-/2020->UAT Testing pending with CG team.
India | TM-AMLOCK | 2lakhs alerts got generated due to duplicate in reference master | 1. 65K Alerts closed, .1.3 lacs alert are pending to exclude for auto supression. 2. Alert Regeneration is in progress. 3. Post Alert generation counts to be shared with Kevin | Awaiting Closure date from ITG | ITG | Siva |  | Priority | FPR VAMSHIDAR and prakash.Same will be initiated from ITG on 17-10-2019. Dependency are there on same as we will generate the alerts in phase wise when the system is free from daily and monthly activities | UPDATED DATA IS PROVIDED IN BACKDATED GENERATION ALERT WISE STATISTICS SHEET | ITG UAT |  | WIP | 03-01-20. Total 9 alerts in line where for 8 alerts generation is completed and still one in progress.Same will be delivered in before 10th Jan 2020
India | TM-AMLOCK | Backdated alert genearation | Backdated alert genearation | Backdated alert genearation for 19 scenarios Rules implemented in April-May 2019. These alerts are to be generated from October 2018. | ITG to generate alerts.ITG propose for front-end | Vamsidhar / Siva |  | CG | Priority | Same is in process,Break up for same is attached in BACKDATED GENERATION ALERT WISE. Out of 9 alerts - | ITG UAT | 2020-01-10 | WIP | 03-01-20. Total 9 alerts in line where for 8 alerts generation is completed and still one in progress.Same will be delivered in before 10th Jan 2020
USA | Pelican | KB Tuning Report has been received from vendor currently under review, queries are been raised with Pelican team for clarification. | UAT to be released by 15 Nov, Go live by 25 Nov | Pending for UAT Delivery. | ITG |  |  | Priority |  | Following up with Pelican and still working on the API tool to process the bulk request | ITG UAT | 2020-01-18 | WIP | UAT to be released by 08 Jan, Go live by 18 Jan
Hongkong | TM-AMLOCK | NRISR file to be treated as a Mandatory file during Upload. | Revised BRS raised on 1st Nov, 2019. FSD sign off given on 18th Nov, 2019. | ITG to share the UAT delivery timeline | ITG |  |  | Priority | FSD in not yet finalised from 3i. FPR:Khushboo(CG),HARI(ITG) | We will deploy the patch in UAT on 28/11/2019 FPR:Khushboo(CG), Hari (ITG) |  |  | Closed
Hongkong | TM-AMLOCK | Transaction monitoring of USD-EURO Clearing transactions: revising the logic to sum of transactions instead of individual transactions Swift transactions flow(MT 202 COV) | BRS raised - make it alert based. BRS shared with ITG on 07 Aug 2019, FSD sign off received | The patch will be delivered on 22nd Nov 2019 by ITG | ITG | Hari | Khushboo | Priority | UAT delivery on 22nd Nov, 2019FPR:Khushboo(CG),HARI(ITG) | We had deployed the patch in UAT on 22/11/2019. FPR:Khushboo(CG), Hari (ITG) Currently in UAT Testing(basic testing at coding level) | CG UAT |  | WIP | 03/01/2020 -> CG UAT PENDING 2 changes pending with vendor-3I for existing logic.
USA | Pelican | Fincen: Changes to consider Active customer List | Fincen Screening to consider all the customers except the closed customers which are closed Prior to one Year. | BRS is shared with ITG. Awaiting delivery date from ITG | ITG | Vamsi |  | Priority |  | We are following up with Pelican and we will update you on this by 25-Nov-2019 | BRS | 2020-01-13 | WIP | Fincen Screening to consider all the customers except the closed customers which are closed Prior to one Year. We are following up with Pelican and we will update you on this by 13-Jan-2020
USA/UK/SG | SAS | Once case is closed without RFI, still we can able to change the status. | Application team will deploy Hotfix as a solution | Awaiting UAT delivery | ITG | Supriya |  | Priority |  | Hotfix 7 is deployed in US Dev environment and the issue regarding below 3 points mentioned in the mail trial are resolved. However there are certain issues and new functionalities & Capability changes that are raised to SAS Consulting & Tech Support team. We will release the setup for UAT once we receive resolution . Observations: 1)Any action will be enabled only on Locking the entity/case- this will disable users to act on same entity / case simultaneously. 2)Analyst unable to add comment on case without edit capability (this would impact the US maker checker approach as edit capability should not be given to Analyst). 3)Accessing notes of a closed case when any entity in triage is opened is resulting in closure event (observed in all Geo)- is not resolved. |  |  | Closed
USA/UK/SG | SAS | Post closure of case, case aging has to stop and freeze. | Application team will deploy Hotfix as a solution | Awaiting UAT delivery | ITG | Supriya |  | Priority |  | Hotfix 7 is deployed in US Dev environment and the issue regarding below 3 points mentioned in the mail trial are resolved. However there are certain issues and new functionalities & Capability changes that are raised to SAS Consulting & Tech Support team. We will release the setup for UAT once we receive resolution . Observations: 1)Any action will be enabled only on Locking the entity/case- this will disable users to act on same entity / case simultaneously. 2)Analyst unable to add comment on case without edit capability (this would impact the US maker checker approach as edit capability should not be given to Analyst). 3)Accessing notes of a closed case when any entity in triage is opened is resulting in closure event (observed in all Geo)- is not resolved. |  |  | Closed
India | NS-AMLOCK | Removal of PEP data : Remiitance and Trade |  | Awatiing Uat Delivery | ITG |  |  | Priority |  | Release in UAT expected on 27-Dec-2019 | ITG UAT | 2019-12-27 | WIP
USA | Pelican | CIB Integration with Business FX | Integration of Business FX with Pelican | Revised BRS to be received from IBG-Product team | ITG | Vamsi |  | Priority |  | We are reviewing the BRS and we are planning to discuss with Compliance team on 26-Nov-2019 | BRS | 2020-01-08 | WIP | We are reviewing the BRS and we are planning to discuss with Compliance team on 08-Jan-2020
Bahrain | TM-AMLOCK | Validation control for exception in alert generation due to missing customer/account details | BRS is shared | Awaiting FSD from 3i-Info tech | ITG | Surya |  | Priority | FSD in not yet finalised from 3i. FPR:Khushboo(CG),HARI(ITG) | We will deploy the patch in UAT on 28/11/2019 FPR:Khushboo(CG), Hari (ITG) 4/12/2019 -> FSD finalized, patch development pending with 3i | BRS | 2019-12-20 | WIP
India | TM-AMLOCK | Tomba Singh: Data extraction of Closed Legacy Alerts where likely true match are closed (DOB/PAN Match) | Replicate the data in temporary db and execute the query instead of production database. | ITG to explore the feasibility and confirm | ITG | Siva |  | Priority | Not feasible,Please close this observation | Not feasible as per Vendor's report. Please close this observation |  |  | Closed
IBG | SAS-ETL | Purging policy for Landing and staging |  |  | ITG |  |  | Priority | Purging Policy will be raised | I-Memo has to be raised by our team. | BRS |  | Open
India | TM-AMLOCK | Office Account Cash transactions upload in a dailly mode. | Office Account Cash transactions upload in a dailly mode. | Office Account transaactions would be enabled in MIS282 format and to be uploaded in Amlock | Moved to Production on Nov | Siva |  | ITG | Priority | UAT is done in 4.3 same can be used for present production , ISSUE:TRASACTIONID IS NOT MATCHED with present production and same is communicated with CG. CR-553-129705, Same is deployed in production on 18/NOV/2019. |  |  | Closed
India | TM-AMLOCK | Testing CCR reporting to FIU for AMLOCK 3.7 | Testing CCR reporting to FIU for AMLOCK 3.7 | UAT testing done.UAT sign off received. | CR-553-128243 , Moved to Production on 11 Oct 2019 | Siva |  | ITG | Priority | CR-553-128243 , Moved to Production on 11 Oct 2019 |  |  | Closed
India | TM-AMLOCK | Auto closure Logic for High Legacy Alerts | Auto Closure Logic for spurt in Legacy Alerts | Pending alerts ,12 lac BRS is shared, FSD signoff provided on 9th aug. Incremental data moved to production on 5th Nov. | Moved to Production | Vishnu / Siva | Vishal | Priority |  | CR-553-129354,Moved to production. Backdated alerts also closed using the same logic. | Live Deployment | 2019-11-05 | Closed
India | TM-AMLOCK | New column "Issuspended" to be incorporate in customer master which is being used for legacy alerts | New column "Issuspended" to be incorporate in customer master which is being used for legacy alerts | 1. Sign off on ETL changes has been given to DWH team to be taken up after 29/JUL/2019 2. Sign off on Amlock Changes is given to Amlock team, to move to production after ETL Changes. 3. One time refresh of Closed customer ids need to be done in Amlock India. | Move to production on 20th August 2019 | Surya / Siva |  | ITG | 2019-08-20 | Move to production on 20th August 2019 |  |  | Closed
India | TM-AMLOCK | 65 alerts auto suppression of false positives | 65 alerts auto suppression of false positives | Requirement shared – Oct 01 Sign off provided on FSD-Jan 04 UAT received-May 15 UAT in process. MErged with Version upgrade and tested in new version. | Merged with Amlock Version Upgrade. Testing in both versions completed successfully | Siva |  |  | Closed | Merged with Amlock Version Upgrade of 4.3. Testing in both versions completed successfully. Same will be in production for 4.3. |  |  | Closed
India | TM-AMLOCK | RAS link is not accessible without user ID | RAS link should be accessible without ID | UAT deployment awaited |  |  |  |  | Closed |  |  |  | Closed
India | TM-AMLOCK | CTR Incremental CTR for November 2018 | Requirement shared for this audit query ITG to find a solution for identifying incremental cash transactions | Approach to be finalised-July end. |  | Siva | Ria |  | Closed | Incremental CTR is given for month of NOV 2018,Same is closed. |  |  | Closed
India | TM-AMLOCK | Large value non-cash transactions in CAA accounts Requirement | CG-Prod to configure the threshold parameters | CG-Prod share timeline |  | Siva / Manohar |  |  | Closed | Moved to production |  |  | Closed
India | TM-AMLOCK | 1.Little or No Withdrawals from account for Business Purposes. live 2.Accounts funded by negotiable instruments in round denominations- configuration pending | Live on August 01, 2019 | Live on August 01, 2019 |  | Siva |  | CG-Product | Closed | Moved to production |  |  | Closed
India | TM-AMLOCK | TBML: Wash Sales rules. Modification & addition of new scenario | Live on August 01, 2019 | Live on August 01, 2019 |  | Siva |  | CG-Product | Closed | Moved to production |  |  | Closed
India | TM-AMLOCK | Productivity Enhancements for TMU: Phase I Customer Search filter Bulk escalate at level one |  | closed |  | Siva |  |  | Closed | Moved to production |  |  | Closed
India | TM-AMLOCK | Modification: Sudden increase in cash deposits in Accounts held by High Risk Customers |  | Closed |  | Siva |  |  | Closed | Moved to production |  |  | Closed
India | TM-AMLOCK | Numerous Low Non Cash Deposit Transactions Leading to Large Accumulation |  | Closed |  | Siva |  |  | Closed | Moved to production |  |  | Closed
India | TM-AMLOCK | New FIU RFI Phase I: 14 Phase II: 4 | Phase I: RFI FIU scenarios – 20-Live Phase II: Dependent on counterparty data, ETL level change | Phase I- closed Phase II- dependent on counterparty data |  |  |  | CG-Product | Priority2 | Phase I- closed Phase II- dependent on counterparty data(SAME IS HOLD AT CG) |  |  | Closed
India | TM-AMLOCK | NTR- section 8 companies | Data received from BIU, under analysis | Aniket from BIU to validate the data and get back |  |  |  | BIU | 2019-10-01 | Pending with CG |  |  | Closed
India | TM-AMLOCK | CBWTR (Cross Border Wire Transfer Report)-Automation | Scoping work in Progress, BRS to be shared |  |  |  |  | CG-Tech | Priority | Yet to be finalised in 4.3 | BRS |  | Open
India | TM-AMLOCK | Missing customer types Issue for Finnacle | BRS Shared on 29th oct | UAT Signed off. Go live date - 19th november |  | Siva |  | DWH |  | One time dump from CRM module customer types is inserted in to AMLOCK system.Automated flow is pending with CG (Toolika) |  |  | Closed
India | TM-AMLOCK | Missing Product type codes in credit cards data | BRS Shared and CR Raised with DWH | Timelines awaited from DWH |  | Siva |  | DWH |  | Development is pending at DWH level and CG yet to finalise the flow |  |  | Closed
Bahrain | NS-AMLOCK | Bahrain NS Error message while file upload UAT | Port Opening |  |  | Naveen |  |  |  | pending at support team for port opening and CG team |  |  | Closed
India | NS-AMLOCK | Matches are coming for NULL value when HULL is screened |  |  |  | Naveen |  |  |  | UAT released signoffpending from CG team |  |  | Closed
Singapore | NS-AMLOCK | AML Analytics Audit. Files prepared for uploading (sg) |  |  |  | Naveen |  |  |  | CG team should inform us on the thematic review | BRS |  | Open
India | NS-AMLOCK | deactivation of denylist for 1Lakh + records India NS and TM |  |  |  | Naveen |  |  |  | 3/12/19->Activity pending with ITG 4/12/19-> Pending with CG for data confirmation | CG UAT |  | Open
India | NS-AMLOCK | 8 reports released to UAT CG team | User was unable to download report from front end |  |  | Naveen |  |  |  | Released in UAT, however CG team needs to know the RCA of the bug fix / issue fix | Live Deployment | 2019-12-25 | Closed
Bahrain | Web Service T & T+1 | Final patch expected in UAT | Post UAT, trial run needs to be run |  |  | Sampath |  |  |  | Patch exppected on 4-Dec-19 | ITG UAT | 2019-12-10 | WIP
India | TM-AMLOCK | Spurt in Legacy alerts | Spurt in Legacy alerts | List Rationalisation Closed customer id and Auto Closure is taken up separately | testing for point 1 and 2 done. ITG to move CR into production. | Surya |  | ITG | Priority2 | CG to revert with details of list, discussion pending | BRS |  | Open | CG to revert with details of list, discussion pending
All geographies | TM-AMLOCK | Multiple Active Directory for Domains | BRS raised on 28th Nov | UAT in progress, will provide URL for CG testing | ITG | Surya |  | Priority |  | We deployed the patch in UAT. Once UAT testing is done by ITG. Same will be confirmed by CG Team | ITG UAT | 2019-12-15 | WIP
All geographies | NS-AMLOCK | Multiple Active Directory for Domains | BRS raised on 28th Nov | UAT in progress, will provide URL for CG testing | ITG | Sravan / Naveen/ Surya/COE Support |  | Priority |  | We deployed the patch in UAT. Once UAT testing is done by ITG. Same will be confirmed by CG Team | ITG UAT |  | WIP
Canada | TM-AMLOCK | Legacy Alert Spurt: 1. Closed Customer ID implementation 2. List Rationalisation | 1) BRS and TC made on 12 July, 2019 CR raised by Canada Compliance. 2) List and BRS shared with ITG on 7Th August | Live deployment done on 13th Nov, 2019 | ITG | Hari |  |  | Live deployment date : 13th Nov, 2019 FPR:Khushboo(CG),Hari,swati(ITG) | Live deployment completed |  |  | Closed
Bahrain | TM-AMLOCK | Bahrain Legacy generation for suspended Customer Id. | Arrange the Fresh full dump of Bahrain Customers . To compare with the 17 Sep dump to identify the count of difference. | Full dump refresh will be done by 21 Nov 2019 | MIS | Hari |  | 2019-11-21 |  | we moved complete customer dump into live |  |  | Closed
Bahrain | TM-AMLOCK | Validation for Exception before Alert generation | BRS raised on 25th sep, 2019. 14-10-2019. FSD sign off given. | UAT in progress | ITG/CG-TECH | Hari |  | Priority |  | We will deploy the patch in UAT on 05/12/2019. FPR:Khushboo(CG), Hari (ITG) | CG UAT |  | WIP | 03/01/2020>> pending with CG
Canada | TM-AMLOCK | Credit card alert generation under 7 alert rules | Data validation going on for bulk upload of files in LIVE. Validation completed for files from Post Date 30th Jul to 20th Aug and alert generation in Daily alert rules. | Need some clarity from ITG for monthly alert rules. | ITG/CG-TECH | Hari |  |  |  | we had uploaded the credit card account,customer and transaction file and we had generated the alerts . we have checked daily rules alerts generation and alerts generated properly . Right now we are checking monthly rules alerts generation. except 2 monthly rules remaing two rules alerts generation is good. | FSD Reviewed |  | WIP | 03/01/2020 ->FSD signoff pending with CG
USA | Pelican | Legacy Alert back end closure: Due to Technical Error Legacy alert got triggered. | Legacy alert generation was disabled due to High FPR, Due to technical issue the alerts got triggered. Post memo approval the alerts need to be closed from back-end. | Post KBTuning it will be released in UAT. | ITG |  | Santosh | Priority |  |  | CR Initiated | 2020-01-08 | WIP | Legacy alert generation was disabled due to High FPR, Due to technical issue the alerts got triggered. Post memo approval the alerts need to be closed from back-end. We need to test this in UAT environment and we will provide the timeliness on this on 08-JAN-2020
UK | NS-AMLOCK | AML Analytics Audit | Awaiting files from AML Analytics | Testing to be carried on 16 DEC 2019 | UK Operations/ITG |  | Vishal | Priority
Canada | TM-AMLOCK | Customer ID Based Rules including change in logic in Rule High Transaction Volume. | BRS raised to ITG. Revised FSD sign off given. | Awatiing issue fix from ITG | ITG | Hari | Khushboo | Priority |  |  | CG UAT |  | WIP | 03/01/2020 ->total 4 alerts rules 2 rules are pending with CG-UAT and 2 rules are pending with 3i
USA | SAS | M2I duplicate SSN counts | Details shared with ITG team. (Covered in row 6) | ITG to check | DWH/ITG | Supriya | Khushboo/Santosh | Priority
USA | SAS | For commercial customer SSN no is appearing instead of TIN no. | Data validation for Existing customer is remaining. M2I tech team need to provide the TIN numer for commercial account number | ITG to refresh the SOLR | ITG |  | Santosh | Priority
India | India-ETL | CBWTR- Credit cards | BRS Shared on 21st august Mapping details received from CC BTG. Validation pending. | Revised Mapping document Awaited | ITG | Rikesh | Toolika | Priority
India | India-ETL | CBWTR - Travel Cards | BRS Shared on 21st august. First draft of mapping document shared by Rikesh. | Revised Mapping document Awaited | ITG | Rikesh | Toolika | Priority
USA/UK/SG | SAS | Unable to retrieve historical transactions at Case Level | Hotfix 7 is deployed in US Dev environment SIT is in progress | Awaiting UAT delivery | ITG | Supriya |  | Priority
Hongkong | TM-Migration | Amlock 4.3 migration | [5 empty] | Priority |  |  | FSD Reviewed |  | WIP | 03-01-20-> FSD signoff pending with CG
Bahrain | TM-AMLOCK | Unable to generate Complete alert report Pending alert report. | New Pending Alerts and Completed Alerts Report for Amlock Bahrain TM. |  |  | Vishnu | Santosh | Priority |  |  | CG UAT |  | WIP | 03-01-20-> UAT pending with CG

## Sheet2 (hidden)
2019-11-01
2019-11-02
2019-11-03
2019-11-04
2019-11-05
2019-11-06
2019-11-07
2019-11-08
2019-11-09
2019-11-10
2019-11-11
2019-11-12
2019-11-13
2019-11-14
2019-11-15
2019-11-16
2019-11-17
2019-11-18
2019-11-19
2019-11-20
2019-11-21
2019-11-22
2019-11-23
2019-11-24
2019-11-25
2019-11-26
2019-11-27
2019-11-28
2019-11-29
2019-11-30
2019-12-01
2019-12-02
2019-12-03
2019-12-04
2019-12-05
2019-12-06
2019-12-07
2019-12-08
2019-12-09
2019-12-10
2019-12-11
2019-12-12
2019-12-13
2019-12-14
2019-12-15
2019-12-16
2019-12-17
2019-12-18
2019-12-19
2019-12-20
2019-12-21
2019-12-22
2019-12-23
2019-12-24
2019-12-25
2019-12-26
2019-12-27
2019-12-28
2019-12-29
2019-12-30
2019-12-31
2020-01-01
2020-01-02
2020-01-03
2020-01-04
2020-01-05
2020-01-06
2020-01-07
2020-01-08
2020-01-09
2020-01-10
2020-01-11
2020-01-12
2020-01-13
2020-01-14
2020-01-15
2020-01-16
2020-01-17
2020-01-18
2020-01-19
2020-01-20
2020-01-21
2020-01-22
2020-01-23
2020-01-24
2020-01-25
2020-01-26
2020-01-27
2020-01-28
2020-01-29
2020-01-30
2020-01-31
2020-02-01
2020-02-02
2020-02-03
2020-02-04
2020-02-05
2020-02-06
2020-02-07
2020-02-08
2020-02-09
2020-02-10
2020-02-11
2020-02-12
2020-02-13
2020-02-14
2020-02-15
2020-02-16
2020-02-17
2020-02-18
2020-02-19
2020-02-20
2020-02-21
2020-02-22
2020-02-23
2020-02-24
2020-02-25
2020-02-26
2020-02-27
2020-02-28
2020-02-29
2020-03-01
2020-03-02
2020-03-03
2020-03-04
2020-03-05
2020-03-06
2020-03-07
2020-03-08
2020-03-09
2020-03-10
2020-03-11
2020-03-12
2020-03-13
2020-03-14
2020-03-15
2020-03-16
2020-03-17
2020-03-18
2020-03-19
2020-03-20
2020-03-21
2020-03-22
2020-03-23
2020-03-24
2020-03-25
2020-03-26
2020-03-27
2020-03-28
2020-03-29
2020-03-30
2020-03-31
2020-04-01
2020-04-02
2020-04-03
2020-04-04
2020-04-05
2020-04-06
2020-04-07
2020-04-08
2020-04-09
2020-04-10
2020-04-11
2020-04-12
2020-04-13
2020-04-14
2020-04-15
2020-04-16
2020-04-17
2020-04-18
2020-04-19
2020-04-20
2020-04-21
2020-04-22
2020-04-23
2020-04-24
2020-04-25
2020-04-26
2020-04-27
2020-04-28
2020-04-29
2020-04-30
2020-05-01
2020-05-02
2020-05-03
2020-05-04
2020-05-05
2020-05-06
2020-05-07
2020-05-08
2020-05-09
2020-05-10
2020-05-11
2020-05-12
2020-05-13
2020-05-14
2020-05-15
2020-05-16
2020-05-17
2020-05-18
2020-05-19
2020-05-20
2020-05-21
2020-05-22
2020-05-23
2020-05-24
2020-05-25
2020-05-26
2020-05-27
2020-05-28
2020-05-29
2020-05-30
2020-05-31
2020-06-01
2020-06-02
2020-06-03
2020-06-04
2020-06-05
2020-06-06
2020-06-07
2020-06-08
2020-06-09
2020-06-10
2020-06-11
2020-06-12
2020-06-13
2020-06-14
2020-06-15
2020-06-16
2020-06-17
2020-06-18
2020-06-19
2020-06-20
2020-06-21
2020-06-22
2020-06-23
2020-06-24
2020-06-25
2020-06-26
2020-06-27
2020-06-28
2020-06-29
2020-06-30